## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column

## Light
PROJECT: Light
Contoso, Ltd. |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Riku Nakano
Project start date: | 2026-01-19 |  |  |  |  | January | [13 empty] | February | [27 empty] | March
Scrolling increment: | 5 | time axis 2026-01-24 to 2026-03-20
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2026-01-24 to 2026-03-20
Project development
Project charter | Goal | Name | 25% | 2026-01-19 | 3
Research | Milestone |  |  | 2026-01-24 | 1 | bar: 2026-01-24
Projections | Low Risk |  | 50% | 2026-01-16 | 10
Stakeholders | Milestone |  |  | 2026-02-08 | 1 | bar: 2026-02-08
Review | Med Risk |  | 10% | 2026-01-25 | 6
Contracts
Proposals | High Risk |  | 60% | 2026-01-25 | 13
Document review | On Track |  | 50% | 2026-01-27 | 9
Bid date | Low Risk |  | 33% | 2026-02-01 | 11
Award date | Milestone |  |  | 2026-02-03 | 1 | bar: 2026-02-03
Finalize |  |  |  | 2026-02-04 | 24
Design
Feasibility study | On Track |  |  | 2026-02-03 | 4
Submit permit applications | Med Risk |  |  | 2026-02-06 | 14
Design proposal | On Track |  |  | 2026-02-21 | 6
Materials | Goal |  |  | 2026-02-25 | 3 | 2026-02-25: 2; 2026-02-26: 2; 2026-02-27: 2
Equipment | Low Risk |  |  | 2026-01-25 | 19
Testing
Environment |  |  |  | 2026-02-28 | 15
System test |  |  |  | 2026-03-14 | 5
Issues/bugs | Milestone |  |  | 2026-04-25 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Dark
PROJECT: Dark
Contoso, Ltd. |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Gupreet Bawa
Project start date: | 2026-01-19 |  |  |  |  | January | [13 empty] | February | [27 empty] | March
Scrolling increment: | 5 | time axis 2026-01-24 to 2026-03-20
Milestone description | Category | Assigned to | Progress | Start | Days | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
TITLE 1
Task 1 | Goal | Name | 25% | 2026-01-19 | 3
Task 2 | Milestone |  |  | 2026-01-24 | 1 | bar: S
Task 3 | Low Risk |  | 50% | 2026-01-16 | 10
Task 4 | Milestone |  |  | 2026-02-08 | 1 | bar: S
Task 5 | Med Risk |  | 10% | 2026-01-25 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2026-01-25 | 13
Task 2 | On Track |  | 50% | 2026-01-27 | 9
Task 3 | Low Risk |  | 33% | 2026-02-01 | 11
Task 4 | Milestone |  |  | 2026-02-03 | 1 | bar: T
Task 5 |  |  |  | 2026-02-04 | 24
TITLE 3
Task 1 | On Track |  |  | 2026-02-03 | 4
Task 2 | Med Risk |  |  | 2026-02-06 | 14
Task 3 | On Track |  |  | 2026-02-21 | 6
Task 4 | Goal |  |  | 2026-02-25 | 3 | W: 2; T: 2; F: 2
Task 5 | Low Risk |  |  | 2026-01-25 | 19
TITLE 4
Task 1 |  |  |  | 2026-02-28 | 15
Task 2 |  |  |  | 2026-03-14 | 5
Task 3 | Milestone |  |  | 2026-04-25 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
Water Project - Snap & Map |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Meghan Carr
Project start date: | 2026-01-19 |  |  |  |  | January | [20 empty] | February | [27 empty] | March
Scrolling increment: | -7 | time axis 2026-01-12 to 2026-03-08
Week & description | Category | Help or Resource | Progress | Start 2026 | Length (days) | time axis 2026-01-12 to 2026-03-08
Week 1 of 7 - Project Setup
Confirm scope, tech stack, & schema | Low Risk | Proposal; AI for 3rd | 75% | 2026-01-12 | 3 | bar: 2026-01-15
Environment setup | On Track | Proposal; prior repos; AI reinf. | 100% | 2026-01-13 | 2 | bar: 2026-01-15
Backend scaffolding | Med Risk | Proposal; prior repos | 85% | 2026-01-14 | 3 | bar: 2026-01-15
Database setup | Milestone | Proposal; prior repos; AI reinf. | 15% | 2026-01-15 | 5 | bar: 2026-01-15 to 2026-01-19
Week 2 of 7 - Core Feature
Photo upload flow | On Track | Proposal; W3 Sch., G2G | 0% | 2026-01-19 | 1 | bar: 2026-01-29
Metadata capture |  |  | 0% | 2026-01-20 | 1 | bar: 2026-01-29
Save submission |  |  | 0% | 2026-01-21 | 1 | bar: 2026-01-29
View saved records |  |  | 0% | 2026-01-22 | 1 | bar: 2026-01-29
Week 3 of 7 | bar: 2026-01-29
AI labeling design |  |  | 0% | 2026-01-26 | 1 | bar: 2026-01-29
AI label suggestions |  |  | 0% | 2026-01-27 | 1 | bar: 2026-01-29
Micro- learning |  |  | 0% | 2026-01-28 | 1 | bar: 2026-01-29
Store AI outputs | Milestone |  | 0% | 2026-01-29 | 1 | bar: 2026-01-29
Week 4 of 7
Submission checks |  |  | 0% | 2026-02-02 | 1 | bar: 2026-02-12
UX refinement |  |  | 0% | 2026-02-03 | 1 | bar: 2026-02-12
Ethics & clarity |  |  | 0% | 2026-02-04 | 1 | bar: 2026-02-12
Accessibility |  |  | 0% | 2026-02-05 | 1 | bar: 2026-02-12
Week 5 of 7 | bar: 2026-02-12
End-to-end testing |  |  | 0% | 2026-02-09 | 1 | bar: 2026-02-12
Data review |  |  | 0% | 2026-02-10 | 1 | bar: 2026-02-12
Performance check |  |  | 0% | 2026-02-11 | 1 | bar: 2026-02-12
MVP criteria check | Milestone |  | 0% | 2026-02-12 | 1 | bar: 2026-02-12
Week 6 of 7
Technical document’n |  |  | 0% | 2026-02-16 | 1
Grant-facing language |  |  | 0% | 2026-02-17 | 1
User guidance |  |  | 0% | 2026-02-18 | 1
Ethics & limits |  |  | 0% | 2026-02-19 | 1
Week 7 - LAST
Final testing |  |  | 0% | 2026-02-23 | 1
Polish MVP |  |  | 0% | 2026-02-24 | 1
Milestone confirmation |  |  | 0% | 2026-02-25 | 1
Phase 1 MVP complete | Milestone |  | 0% | 2026-02-26 | 1
To add more data, Insert new rows ABOVE this one