## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column

## Color
Water Project - Snap & Map |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Meghan Carr
Project start date: | 2026-01-12 |  |  |  |  | January | [20 empty] | February | [27 empty] | March
Scrolling increment: | 0 | time axis 2026-01-12 to 2026-03-08
Week & description | Category | Help or Resource | Progress | Start 2026 | Length (days) | time axis 2026-01-12 to 2026-03-08
Week 1 of 7 - Project Setup | bar: 2026-01-22; 2026-01-24 to 2026-01-25
Confirm scope, tech stack, & schema | On Track | Proposal; AI for 3rd | 100% | 2026-01-12 | 3 | bar: 2026-01-22; 2026-01-24 to 2026-01-25
Environment setup | On Track | Proposal; prior repos; AI reinf. | 100% | 2026-01-13 | 2 | bar: 2026-01-22; 2026-01-24 to 2026-01-25
Backend scaffolding | On Track | Proposal; prior repos | 100% | 2026-01-14 | 3 | bar: 2026-01-15; 2026-01-22; 2026-01-24 to 2026-01-25
Database setup | Low Risk | Proposal; prior repos; AI reinf. | 30% | 2026-01-15 | 12 | bar: 2026-01-15; 2026-01-24 to 2026-01-25
Week 2 of 7 - Core Feature | bar: 2026-01-22; 2026-01-24 to 2026-01-25
Photo upload flow | On Track | Proposal; W3 Sch., G2G | 100% | 2026-01-19 | 4 | bar: 2026-01-22; 2026-01-24 to 2026-01-25; 2026-01-29
Metadata capture | High Risk | EXIF; | 5% | 2026-01-20 | 7 | bar: 2026-01-24 to 2026-01-25; 2026-01-29
Save submission | High Risk | Cache | 5% | 2026-01-21 | 6 | bar: 2026-01-24 to 2026-01-25; 2026-01-29
View saved records & Model PROTOTYPE | Milestone | Staff Support | 50% | 2026-01-22 | 3 | bar: 2026-01-22 to 2026-01-25; 2026-01-29
Week 3 of 7 | bar: 2026-01-24 to 2026-01-25; 2026-01-29
AI labeling/description design | Low Risk | Done w/ Model_RAG… Line 8 & 13? | 50% | 2026-01-21 | 2 | bar: 2026-01-29
AI label/description suggestions | Low Risk | Done w/ Model_RAG… Line 8 & 13? | 50% | 2026-01-22 | 1 | bar: 2026-01-29
Micro-learning | Low Risk | Done w/ Model_RAG… Line 8 & 13? | 100% | 2026-01-21 | 2 | bar: 2026-01-29
Store AI outputs | Milestone |  | 15% | 2026-01-29 | 3 | bar: 2026-01-29 to 2026-02-01
Week 4 of 7
Submission checks |  |  | 0% | 2026-02-02 | 1 | bar: 2026-02-12
UX refinement |  |  | 0% | 2026-02-03 | 1 | bar: 2026-02-12
Ethics & clarity |  |  | 0% | 2026-02-04 | 1 | bar: 2026-02-12
Accessibility |  |  | 0% | 2026-02-05 | 1 | bar: 2026-02-12
Week 5 of 7 | bar: 2026-02-12
End-to-end testing |  |  | 0% | 2026-02-09 | 1 | bar: 2026-02-12
Data review |  |  | 0% | 2026-02-10 | 1 | bar: 2026-02-12
Performance check |  |  | 0% | 2026-02-11 | 1 | bar: 2026-02-12
MVP criteria check | Milestone |  | 0% | 2026-02-12 | 1 | bar: 2026-02-12
Week 6 of 7
Technical document’n |  |  | 0% | 2026-02-16 | 1
Grant-facing language |  |  | 0% | 2026-02-17 | 1
User guidance |  |  | 0% | 2026-02-18 | 1
Ethics & limits |  |  | 0% | 2026-02-19 | 1
Week 7 - LAST
Final testing |  |  | 0% | 2026-02-23 | 1
Polish MVP |  |  | 0% | 2026-02-24 | 1
Milestone confirmation |  |  | 0% | 2026-02-25 | 1
Phase 1 MVP complete | Milestone |  | 0% | 2026-02-26 | 1
To add more data, Insert new rows ABOVE this one